## Sprints
Sprint | Week | Sprint Goal | Start Date | End Date | Sprint State
1 | 2/3 | Draft SRS, Use case diagrams | 2024-04-30 | 2024-05-11 | Closed
2 | 4/5 | Draft SRS, System requirements for functional requirements | 2024-05-14 | 2024-05-25 | Active
3 | 6/7 |  | 2024-05-28 | 2024-06-08 | Inactive
MST + Term Break
4 | 12/13 |  | 2023-01-02 | 2023-01-13 | Inactive
5 | 14/15 |  | 2023-01-16 | 2023-01-27 | Inactive
6 | 16/17 |  | 2023-01-30 | 2023-02-10 | Inactive
Formulas:
End Date = [Start Date]+11
Start Date = [Start Date, row above]+14

## Active Sprint Board (hidden)
To Do | Doing | Done

## Product Backlog
ID | Story Title | Story Description | Definition of Done | Estimated Effort (hours) | Actual Effort (hours) | Status | Sprint
1 | Create Use Case Diagrams in SRS document | As a Software Developer, I need to define all the different Use Case Diagrams for the Library System | All necessary Use Case Diagrams are defined in the SRS document SRS document is commited and pushed to Github | 4 | 5 | Done | Sprint 1
2 | Create System Requirements in SRS document | As a Software Developer, I need to define all the different System Requirements for the Library System | All necessary System Requirements are defined in the SRS document SRS document is commited and pushed to Github | 3 |  | Doing | Sprint 2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95 | [5 empty] | Doing
96
97
98
99
100

## enum (hidden)
Sprint | Start Date | End Date | Story Status | Spint State
Sprint 1 |  |  | To Do | Inactive
Sprint 2 |  |  | Doing | Active
Sprint 3 |  |  | Done | Closed
Sprint 4
Sprint 5
Sprint 6